## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Backend1 | 07-Feb-2026 | Inconsistent date parsing observed for RECEIVED_DATE and DECISION_DATE fields in input dataset | Sprint 1 | Backend2 | Logical | Standardized date parsing and validated ingestion conversion | 08-Feb-2026 | Closed | Verified during Sprint 1 preprocessing rerun
2 | Backend1 | 22-Feb-2026 | EDA visualization failed when VISA_CLASS is imbalanced. | Sprint 2 | Backend2 | Logical | Added empty-slice guard before plotting | 23-Feb-2026 | Closed | Visualization pipeline stabilized
3 | Backend2 | 08-Mar-2026 | Model evaluation metrics showed variation across runs due to preprocessing inconsistencies | Sprint 3 | Backend4 | Standards | Fixed random_state and unified validation split | 09-Mar-2026 | Closed | Comparison metrics became reproducible
4 | Frontend1 | 20-Mar-2026 | Frontend validation failed for wage inputs containing comma-separated values | Sprint 4 | Frontend1 | User Interface | Added numeric input normalization before API submission | 21-Mar-2026 | Closed | Form now accepts formatted income values
5 | Backend1 | 2026-03-24 | API returned non-descriptive error when mandatory input fields were missing | Sprint 4 | Backend2 | Maintainability | Implemented field-level validation with clear messages | 28-Mar-2026 | Closed | Error handling is now traceable and user-friendly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others